## Sheet1
Iteration 1, 4 weeks, May 18 - June 12 |  |  | Iteration 2, 4 weeks, June 15 - July 10 |  |  | Iteration 3, 4 weeks, July 13 - August 7
UC01 - Do One Points: 3 Priority: 1 Depends On: None | UC02 - Do Two Points: 3 Priority: 1 Depends On: UC01 | UC03 - Do Three Points: 6 Priority: 2 Depends On: UC02 | UC04 - Do Four Points: 2 Priority: 5 Depends On: None | UC05 - Do Five Points: 2 Priority: 5 Depends On: None | UC06: Do Six Points: 8 Priority: 3 Depends On: UC02, UC03 | UC07: Do Seven Points: 5 Priority: 4 Depends On: UC03 | UC08: Do Eight Points: 2 Priority: 3 Depends On: UC03 | UC09 - Do Nine Points: 5 Priority: 4 Depends On: UC03
| Risk 1 |  | Risk 2 |  | Risk 3 |  | Risk 4 |  | Risk 5
Risk | UC03 could have mistakes or issues, which could lead to the hinderance of other use cases depending on it. |  | Client could request changes to development processes that have already been completed. |  | Developers could be running behind on programming process. |  | A client change requirement could result in one use case being dependent on another when that wasn't the case before. |  | Testers could run into issues during the final steps of the production process.
Risk Resolution Measures | Developers who depend on UC03 could work with that's been given while modifications are made. |  | Make modifications to the project to reduce work in certain areas in order to produce new requirements without affecting timeline. |  | Developers could utilize preexisting codes and modify them or work together to complete required work. |  | The use case that becomes necessary for the development of another would be completed as soon as possible. |  | Allow for testers to conduct their testing throughout the production process as developers finish working.
Justification | This resolution measure would prevent too much lost time from accumulating and causing a real disturbance in the production process. |  | This resolution measure would allow for more flexibility from clients without affecting the estimated arranged timeline. |  | This resolution measure could allow for work to be completed as expected in the expected timeline created. |  | This resolution measure would attempt to restructure the priority listing in order to keep the production process moving smoothly. |  | This resolution measure would allow for mistakes to be caught early and fixed to prevent any losses.